## Sheet1
|  | Project Name: | A To-Do list web application.
|  | Project Description: | An application a user can interact with via a website to view and create To-Do lists.
|  | Project Owner: | Leighton Manning
Risk ID | Date registered | Risk area | Risk description | Probability |  | Risk Level |  | Project impact | Proximity / Length of impact | Response strategy
1 | 03.02.21 | covid-19 | Global pandemic. Virus which has the potential to make you very ill. |  | x |  | x | Having to work completely virtual and also the potential of getting ill. | Untill the pandemic ends. | Following the local lock down rules for my area. Getting used to working completley virtual.
2 | 03.02.21 | Hardware issues | Always a potential that the current hardware setup(PC/MONITOR) may stop working or need to be replaced | x |  |  | x | Would result in having to replace the hardware which could take time away from the project. | Untill hardware has been replaced. | Making sure to check hardware daily for any faults or potential issues that could arise.
3 | 03.02.21 | File loss | Meaning if important bits of my project are lost/corrupted/deleted. | x |  |  | x | Could have a big impact depending on what was lost. | Untill the file has been replaced or recovered. | Making sure all files are backed up physically and also on the cloud. Github will help with version control aswell.
4 | 03.02.21 | Google cloud issues | Google cloud could be down or not working for the time I need it. | x |  |  | x | Could have an impact due to my prtogram not being able to connect to the database. | Untill google cloud platform comes back online. | Keeping an eye out for any planned outages or down time.
5 | 03.02.21 | Power outage | Electricity outage would mean I was unable to use my computer. | x |  | x |  | Could either make me lose work if I was in the middle of working. Or not be able to present/show my project due to not being able to use the pc. | Untill electricity comes back. | Keep my work backed up at all times using git so that if there is a power issue then my work is saved.
6 | 03.02.21 | Internet connection drop. | There could be an issue with my internet speeds being slow or not connecting | x |  |  | x | This would make it difficult to work on my project especially with the git updates and SQL database. | As long as the internt is down/going slow. | Check internet speeds daily. Making sure my computer is hard wired in to the internet at all times. Having backup 4G internet
1
1
1